| 16 STEPS for developing a Wetland Observatory | Example : The Mediterranean Wetlands Observatory | Remarks |
| --- | --- | --- |
| - Giving the mandate / authority to an organization (or consortium) | - From the MedWet Initiative, who entrusted TdV to develop it as a service to its 27 constituting members | In order to gather the support from the local actors for the idea of an observatory, prior to defining anything; maximizes your chances for finding support (money/manpower) and a willing, long-term host organization. |
| - Delineating the perimeter of the Observatory : both thematic (wetlands only ? biodiversity ? the environment ?), and geographical | - Wetlands in the Ramsar sense - 27 MedWet countries , their Med and non-Med parts alike | likely to be determined by the (political) mandate of the organisation (or consortium) |
| - Defining Objectives and Targets (i.e. end-users of results) | Objectives : - To analyse the status and trends of Mediter-ranean wetlands, including their biodiversity, the goods and services that they deliver and the environmental factors and anthropogenic pressures that explain their status and trends; - To promote effective decision-making for the protection, restoration, wise use and sustainable management of Mediterranean wetlands. Targets - Decision-makers (national, local and internat’l) - The general public through the media (as an indirect way to also influence decision-makers). |  |
| - Defining the principles of the Observatory | Principles of efficiency: - Efficiency/ effectiveness - Long-term sustainability Working principles : - Partnerships - responding to users/countries needs - Communication and transfer of all results |  |
| - A logical framework for the Observatory | DPSIR model (Drivers-Pressures-State-Impacts-Responses) : See Fig 1. below |  |
| - Defining the specific themes to achieve the objectives | 5 Themes : - Biodiversity (species - ecosystems); - Water - Ecological services - Pressures on wetlands and Drivers (i.e. underlying causes); - Responses to wetland loss and degradation |  |
| - Identify and list all relevant monitoring efforts already ongoing, and by who | Literature and Internet searches; queries to TDV networks | Existing monitoring efforts should be identified and included in the co-development process, to facilitate a maximum of engagement and avoid potential conflicts in the future. |
| - Governance and partnership structure | See Fig 2 below |  |
| - Defining a communication strategy (which tools/ format for which targets ?) | A strategy planned the various outputs and their issuing timetable | Needs to be defined from the start, not at the end |
| - Defining the indicators | 25 indicators selected, 16 currently monitored | Must not come too early in the process |
| - Methods for regular monitoring of indicators | Precisely described in the Annex to all MWO2 Indicator Factsheets : https://tourduvalat.org/en/media/brochures/ |  |
| - Planning data storage (+ integration with other relevant datasets?) | Insufficiently planned from the start, except for Biodiversity (integration of LPI data to global databases, when allowed by data producers |  |
| - Collecting and storing data, and calculating indicator values (by one or more partners) | - MWO = Limited field monitoring: mainly satellite image analysis, compilation of data from literature, public databases and personal contacts, application of models… - Developing MWO database (ongoing) | Note : the parameters collected in the field are not necessary the indicators themselves (but should contribute to them) |
| - Analysing data | - Currently, indicator by indicator : cf. analysis in MWO2 indicator Factsheets: https://tourduvalat.org/en/media/brochures/ - Ultimately : cross-analysis of different MWO indicators/ themes |  |
| - Communicating and disseminating the results | MWO1/MWO2 reports ; Website (MWO1 only; no longer) ; scientific papers; presentations and events in both scientific and conservation conferences; partnering with MedWet as a relay… |  |
| - Evaluating the Observatory’s functioning and impact, and develop recommend-dation for improvements if necessary | MWO evaluations in 2013 & 2018 (mid-term evaluations of TDV 5-years Plans) |  |

IN SHORT : The 16 steps for developing a Wetland Observatory

1.	Mandate

2.	Scope : thematic  and geographical

3.	Objectives and Targets

4.	The principles

5.	Logical framework

6.	Themes

7.	Identify existing, relevant monitoring

8.	Governance and partnership structure

9.	Communication/ Transfer strategy

10.	Indicators

11.	Methods & Protocoles

12.	Planning data storage

13.	Collecting data and calculating indicator values

14.	Data analysis

15.	Communication and dissemination of results

16.	Evaluation  & Adaptation

Fig. 1.

Fig 2 (Governance model - slightly changed  since then)

Unité de Coordination

(TdV)

Gouvernance

Partenaires techniques & institut.

Gestion exécutive

Comité de Pilotage de Medwet

Groupe de Conseil (MW/ Com)

Incl.  quelques partenaires et utilisateurs

Protocole

Conventions

Partenaires Financiers

Partenariats (au sens large)

UTILISATEURS

Feed-back